Capstone Project Report

Report 2 – Project Management Plan

Battery-Aware Mission Planner (BAMP)

A Decision-Support System for Energy Consumption Prediction in Surveillance Drones

Class: IS1904        Supervisor: Assoc.Prof. Ngô Đăng Hà An

Group: Trương Quốc Tuấn (Leader); Lê Vương Định; Nguyễn Trường Huy; Võ Minh Thuận; Nguyễn Ngọc Phương Anh

– Ho Chi Minh City, September 2026 –

Table of Contents

I. Record of Changes	3

II. Project Management Plan	4

1. Overview	4

1.1 Scope & Estimation	4

1.2 Project Objectives	4

1.3 Project Risks	4

2. Management Approach	5

2.1 Project Process	5

2.2 Quality Management	5

2.3 Training Plan	5

3. Project Deliverables	5

4. Responsibility Assignments	5

5. Project Communications	6

6. Configuration Management	6

6.1 Document Management	6

6.2 Source Code Management	6

6.3 Tools & Infrastructures	6

# I. Record of Changes

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 08-Sep-2026 | A | Whole team | Initial draft of Report 2 - Project Management Plan. |

*A - Added M - Modified D - Deleted

# II. Project Management Plan

## 1. Overview

### 1.1 Scope & Estimation

The table below breaks down the BAMP feature set into the WBS items already tracked in Report3_Project_Tracking.xlsx, rated Simple/Medium/Complex per the convention below, using the template's own default man-day mapping (Simple=4, Medium=7, Complex=10) as a planning estimate to be refined by the team during WP4 sprint planning.

Why the four Complex items cost 10 days each: Mission Builder is the only screen with dynamic, ordered sub-records (add/edit/remove flight legs) plus embedded weather and model-selection controls (SRS 3.3.1). Prediction Engine must load a version-locked model artifact and run leg-level inference in a way that stays traceable per BR-02. Simulation & Feasibility Results and Drone Comparison View both re-run the full prediction pipeline (per leg, then per drone) rather than reading one stored result – that repeated computation, not the UI, is what puts them on par with Mission Builder despite simpler screens.

| # | WBS Item | Complexity | Est. Effort (man-days) |
| --- | --- | --- | --- |
| 1 | Drone Management |  | 8 |
| 1.1 | Drone List / Selection | Simple | 4 |
| 1.2 | Custom Drone Form | Simple | 4 |
| 2 | Mission Configuration |  | 17 |
| 2.1 | Mission Builder | Complex | 10 |
| 2.2 | Flight Leg Editor (popup) | Medium | 7 |
| 3 | Weather Configuration |  | 4 |
| 3.1 | Weather Form | Simple | 4 |
| 4 | Prediction |  | 24 |
| 4.1 | Model & Version Selection | Medium | 7 |
| 4.2 | Prediction Engine (service) | Complex | 10 |
| 4.3 | AI Explanation Client (service, Tier 2) | Medium | 7 |
| 5 | Simulation |  | 10 |
| 5.1 | Simulation & Feasibility Results | Complex | 10 |
| 6 | Comparison |  | 10 |
| 6.1 | Drone Comparison View | Complex | 10 |
| 7 | Scenario Management |  | 7 |
| 7.1 | Scenario Manager | Medium | 7 |
| 8 | Data (non-screen) |  | 7 |
| 8.1 | Model Registry Service | Medium | 7 |
| Total Estimated Effort (man-days) |  |  | 87 |

### 1.2 Project Objectives

The project's overall objective is to deliver a working, statistically validated BAMP application (Tier 1 MVP committed; Tier 2 extensions if schedule allows) together with the research documentation required for the capstone defense, on the schedule defined in Section 3. Specific target metrics proposed below are planning targets to be reviewed with the supervisor; they are not yet measured results.

Quality

| # | Testing Stage | Test Coverage | No. of Defects | % of Defect | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Reviewing | 100% SRS/SDS peer-reviewed | 0 major open issues at submission | - | Peer review checklist per report |
| 2 | Unit Test | ≥ 80% (core logic) | TBD after WP4 | TBD | pytest (FastAPI backend) |
| 3 | Integration Test | 100% REST endpoints | TBD after WP4 | TBD | API contract tests |
| 4 | System Test | 100% UCs, ≥ 1 case each | TBD after WP5 | TBD | Manual + scripted test cases |
| 5 | Acceptance Test | 100% Tier-1 MVP demoed | TBD after WP5 | TBD | Live demo, WP5 milestone |

Milestone Timeliness (%): Target 100% of Report 1-7 milestones (Section 3) delivered by their due date; a milestone slipping more than 3 working days is escalated to the supervisor.

Allocated Effort (man-days): Application development (WP4) = 87 man-days (Section 1.1); remaining effort across requirement engineering (WP1), data engineering (WP2), model development (WP3), evaluation/QA (WP5), and documentation (WP6) to be tracked in Report3_Project_Tracking.xlsx as work progresses.

### 1.3 Project Risks

The risks below are carried over from the approved Capstone Project Register, with Impact/Possibility ratings added for planning purposes.

Rating logic: Impact reflects how much the MVP commitment (Report 1, Section 6.1) would be undermined if the risk materializes uncontrolled; Possibility reflects how likely it is to occur given the team's data, schedule, and dependencies as of this report. Risks #5 (Scope) and #8 (Schedule) are rated High Impact because either one directly threatens the Tier 1 MVP due date (Section 3); #1 (Data) is rated High Possibility because the 209-flight, single-platform limit is already a present constraint, not a future possibility.

| # | Risk Description | Impact | Possibility | Response Plans |
| --- | --- | --- | --- | --- |
| 1 | Data risk: available telemetry data is limited to 209 flights from a single quadcopter platform (CMU KiltHub). | Medium | High | Tier 1 MVP trains/validates on this dataset only (sufficient for Sub-RQ1/2); a supplementary fixed-wing dataset (IDF-DS) may be used as a non-committed external validation check only. |
| 2 | Version management risk: inconsistent results if model artifacts/version metadata change without traceability. | Medium | Low | Register model versions explicitly; keep registered versions immutable; record model+version with every result (BR-02). |
| 3 | Model risk: prediction models may not generalize to drone configurations or conditions outside the training data range. | Medium | Medium | Cross-validation, error analysis, explicit out-of-range warnings in the UI (BR-03). |
| 4 | Statistical validity risk: small number of CV folds may limit statistical power to detect a genuine difference between models. | Low | Medium | Report this limitation explicitly; interpret non-significant results as inconclusive, not as equivalence. |
| 5 | Scope risk: several features (real-time telemetry, live weather API, mobile app, automated drone selection) are explicitly out of scope. | High | Medium | Maintain a clear MVP boundary; escalate scope questions to the supervisor before implementation. |
| 6 | External API dependency risk: AI-based explanation feature depends on a third-party AI API (cost, rate limits, latency, availability, credential handling). | Low | Medium | Treat as Tier 2 extension (not required for MVP); template-based fallback; cache/reuse explanations to reduce call volume (BR-07). |
| 7 | Multiple-comparison risk: comparing four models increases the number of pairwise statistical tests, raising false-positive risk. | Low | Medium | Test each additional model individually against the LR baseline rather than exhaustive all-pairs comparison. |
| 8 | Schedule risk: model development (WP3) and application development (WP4) need to proceed in parallel. | High | Medium | WP structure with milestone reviews; prioritize the core simulation workflow over comparison/what-if if time is constrained. |

## 2. Management Approach

### 2.1 Project Process

The team follows an iterative, work-package-driven process, similar in structure to the Report 2 Sample Project Schedule: each Work Package (WP1-WP6, as defined in the Capstone Project Register) produces a milestone deliverable, and WP4 (Application Development) is further broken into short code iterations (iteration = a subset of Tier 1/Tier 2 features, each ending with code + unit/integration testing), so that a working increment of the application exists throughout development rather than only at the end. Requirement (WP1) and data/model work (WP2-WP3) proceed largely in parallel with early application scaffolding (WP4), consistent with the Schedule risk mitigation in Section 1.3.

### 2.2 Quality Management

- Defect Prevention – coding standards enforced via linters (ESLint/Prettier for Next.js/TypeScript, Ruff/Black for FastAPI/Python); mandatory pull-request review before merging to the develop branch.

- Reviewing – every report (SRS, SDS, etc.) and major design decision is peer-reviewed by at least one other member before submission; see the Responsibility Assignment matrix in Section 4 for review ownership.

- Unit Testing – pytest for the FastAPI backend and prediction/simulation logic; Jest/React Testing Library for Next.js components; target coverage in Section 1.2.

- Integration Testing – automated tests against the FastAPI REST endpoints (request/response contracts, database interactions via SQLAlchemy) run in the local Docker Compose environment.

- System Testing – end-to-end manual and scripted test cases covering all 11 use cases from the SRS (Report 3), executed against the full Docker Compose stack before each milestone demo.

### 2.3 Training Plan

The team assessed its skills against the confirmed technology stack (Next.js/TypeScript, FastAPI/Python/Pydantic, PostgreSQL/SQLAlchemy/Alembic, scikit-learn/joblib, Docker Compose) and did not identify any mandatory training needs; all members are already proficient in these tools. The table below is kept for reference and will be updated if a skill gap is identified during WP3/WP4.

| Training Area | Participants | When, Duration | Waiver Criteria |
| --- | --- | --- | --- |
| N/A | N/A | N/A | Not required |

## 3. Project Deliverables

Project start: 07/09/2026 (confirmed). The master schedule below follows the Work Packages defined in the Capstone Project Register (WP1-WP6) and the Report 1-7 cadence used by this template; dates are computed from the confirmed start date on a standard weekly cadence and should be reconciled with official FAP/LMS deadlines once published.

| # | Deliverable | Due Date | Notes |
| --- | --- | --- | --- |
| 1 | Report 1 - Project Introduction | 11/09/2026 | WP1 kickoff |
| 2 | Report 2 - Project Management Plan | 18/09/2026 | This document |
| 3 | Report 3 - Software Requirement Specification (SRS) | 25/09/2026 | Delivered 08/09/2026 (ahead of schedule) |
| 4 | Curated dataset & Data Dictionary (WP2) | 09/10/2026 | Data Engineering |
| 5 | Report 4 - Software Design Specification (SDS) | 09/10/2026 | WP1 SRS → WP4 design handoff |
| 6 | Trained models & Comparative Evaluation Report (WP3) | 30/10/2026 | LR/RF committed; XGBoost/GB if schedule allows |
| 7 | Working Application - Tier 1 MVP (WP4) | 20/11/2026 | Drone Mgmt, Mission Config, Prediction, Simulation |
| 8 | Report 5 - Test Report (WP5) | 27/11/2026 | Functional + usability testing |
| 9 | Report 6 - User Guide (WP6) | 04/12/2026 |  |
| 10 | Report 7 - Final Project Report & Presentation (WP6) | 18/12/2026 | Final defense package |

## 4. Responsibility Assignments

Since all members are full-stack capable, the split below assigns a PRIMARY owner per responsibility for accountability; members support each other across areas as needed.

How this works day to day: the Doer (D) drafts or implements and is accountable for the deliverable; Reviewers (R) sign off before submission per the Reviewing practice in Section 2.2; Supporters (S) are consulted for domain input but do not block progress. A disagreement between a Doer and a Reviewer that the two cannot resolve is escalated to TuanTQ (Leader) as final internal decision-maker; an unresolved technical or scope question goes to the Supervisor at the next Bi-weekly Review (Section 5).

D~Do; R~Review; S~Support; I~Informed; <blank>- Omitted

| Responsibility | TuanTQ (Leader) | DinhLV | HuyNT | ThuanVM | AnhNNP |
| --- | --- | --- | --- | --- | --- |
| Project Planning & Tracking | D | S | S | S | S |
| Prepare Report 1 (Project Introduction) | D | R | R | R | R |
| Prepare Report 2 (Project Management Plan) | D | R | R | R | R |
| Prepare Report 3 (SRS) | D | S | R | S | R |
| Prepare Report 4 (SDS) | R | D | R | S | S |
| Data Engineering (WP2: cleaning, feature engineering) | R | S |  | D | S |
| Model Development & Evaluation (WP3) | R | S |  | D | S |
| Backend Development (FastAPI, PostgreSQL, SQLAlchemy) | S | D |  | S | S |
| Frontend Development (Next.js, Tailwind, Recharts) | S | S |  |  | D |
| DevOps & Deployment (Docker Compose) | S | S |  | D | S |
| QA & Testing (Test Plan, Test Cases, Defect Tracking) | S | S | D | S | S |
| Documentation & User Guide (Report 6) | R | S | D | S | S |
| Final Report & Presentation (Report 7) | D | S | S | S | S |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Weekly Team Sync | Whole team | Progress update, blocker resolution, task re-planning | Weekly (proposed - to confirm) | Google Meet + Report3_Project_Tracking.xlsx |
| Supervisor Review | Team + Supervisor (Assoc.Prof. Ngô Đăng Hà An) | Milestone review, scope/decision confirmation (e.g., BR margins, WP1 rule-based approach) | Bi-weekly (proposed) + at each Report milestone | Google Meet / in-person + email |
| Report Submission | Supervisor / FAP | Formal deliverable submission (Report 1-7) | Per milestone (Section 3) | FAP portal / email + Google Drive link |
| Issue / Defect Tracking | Whole team | Log and track issues, defects, and open questions | Continuous, as they arise | Report3_Project_Tracking.xlsx (Issues/Defects/Q&A tabs), shared on Google Drive |
| Code Review | Developer + Reviewer | Pull request review before merge to develop branch | Per pull request | GitHub Pull Requests |

## 6. Configuration Management

### 6.1 Document Management

All project documents (reports, diagrams, meeting notes) are kept in a shared Google Drive folder, structured by Work Package/Report number (e.g., /Report1, /Report2, ... /Report7, /Diagrams). Reports are drafted collaboratively in Google Docs and converted to the official DOCX template format before submission. Each submitted version is named with the report number and date (e.g., Report3_SRS_v1_2026-09-08.docx) and logged in that report's Record of Changes table.

### 6.2 Source Code Management

Source code is managed in a private GitHub repository. The team uses a main/develop/feature-branch workflow: feature branches are created per task, merged into develop via a reviewed Pull Request (Section 2.2), and develop is merged into main at each completed iteration/milestone. Commit messages follow a short conventional format (e.g., feat:, fix:, docs:). The local development/deployment environment (frontend, backend, and PostgreSQL database) is defined in a docker-compose.yml so every member runs an identical stack.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Next.js, TypeScript, Tailwind CSS, Recharts (Frontend); FastAPI, Python, Pydantic (Backend) |
| Database | PostgreSQL, SQLAlchemy (ORM), Alembic (migrations) |
| Machine Learning | scikit-learn, joblib (saving/loading trained model artifacts) |
| Local Development / Deployment | Docker Compose |
| IDEs/Editors | Visual Studio Code [assumption - confirm with team] |
| Diagramming | draw.io (diagrams.net) - see BAMP_Diagrams.drawio from Report 3 |
| Documentation | MS Office / Google Docs, Sheets, Slides |
| Version Control | GitHub (Source Code), Google Drive (Documents) |
| Project Management | Report3_Project_Tracking.xlsx (WBS, Issues, Defects, Q&A), Google Drive |